## 1. Addendum
Addenda or use of contingencies | [9 empty] | FOR INTERNAL USE ONLY
No. of contract:
Contract performance period: 1 April 2023 until 30 September 2025
|  | Budget as per contract/last addendum signed |  |  |  | Use of contingencies / addenda | Budget as per new addendum signed |  |  | Variations compared to the current budget |  | Justification for variations
Expenditures |  | Units | # Units | Unit value (EUR) | Total Costs (EUR) |  | # Units | Unit value (EUR) | Total Costs (EUR) | Absolute values (EUR) | %
|  |  | (a) | (b) | (a)*(b) |  | (a) | (b) | (a)*(b) | g=f-c | h=(g/c)*100
1 | Human Resources
1.1 | Salaries (gross salaries including social security charges and other related costs, local staff)
1.1.1 | Technical
1.1.1.1 | Project coordinator (100%) - Partner B | Per month | 30 | 776 | 23280 | -6208 | 22 | 776 | 17072 | -6208 | -26.67%
1.1.1.2 | Project coordinator (100%) - Partner A | Per month | 30 | 776 | 23280 | 3880 | 35 | 776 | 27160 | 3880 | 16.67%
1.1.1.3 | Project officer (100%) - Partner B | Per month | 30 | 360 | 10800 | 1800 | 35 | 360 | 12600 | 1800 | 16.67%
1.1.1.4 | Project officer (100%) - Partner A | Per month | 30 | 360 | 10800 | 1800 | 35 | 360 | 12600 | 1800 | 16.67%
1.1.1.5 | MEAL officer (50%) - Partner B | Per month | 15 | 450 | 6750 | 9000 | 35 | 450 | 15750 | 9000 | 133.3%
1.1.1.6 | MEAL officer (50%) - Partner A | Per month | 15 | 450 | 6750 | 9000 | 35 | 450 | 15750 | 9000 | 133.3%
1.1.1.7 | Field officers (6 staff at 100%) - Partner B | Per month | 180 | 240 | 43200 | 0 | 180 | 240 | 43200 | 0 | 0%
1.1.1.8 | Field officers (6 staff at 100%) - Partner A | Per month | 180 | 240 | 43200 | 0 | 180 | 240 | 43200 | 0 | 0%
1.1.1.9 | Communication and Media officer (80%) - Partner B | Per month | 24 | 204 | 4896 | 0 | 24 | 204 | 4896 | 0 | 0%
1.1.1.10 | Communication and Media officer (80%) - Partner A | Per month | 24 | 204 | 4896 | 0 | 24 | 204 | 4896 | 0 | 0%
#VALUE!
1.1.2 | Administrative/support staff |  |  |  |  | #VALUE!
1.1.2.1 | Finance and administrative officer (50%) - Partner B | Per month | 15 | 450 | 6750 | -2250 | 10 | 450 | 4500 | -2250 | -33.33%
1.1.2.2 | Finance and administrative officer (50%) - Partner A | Per month | 15 | 450 | 6750 | 0 | 15 | 450 | 6750 | 0 | 0%
1.1.2.3 | Finance and administrative assistant (80%) - Partner B | Per month | 24 | 230 | 5520 | 0 | 24 | 230 | 5520 | 0 | 0%
1.1.2.4 | Finance and administrative assistant (80%) - Partner A | Per month | 24 | 230 | 5520 | 0 | 24 | 230 | 5520 | 0 | 0%
#VALUE!
1.2 | Salaries (gross salaries including social security charges and other related costs, expat/int. staff) |  |  |  |  | #VALUE!
#VALUE!
1.3 | Per diems for missions/travel |  |  |  |  | #VALUE!
1.3.1 | Abroad (staff assigned to the Action) |  |  |  |  | #VALUE!
1.3.1.1 | Abroad perdiem - Partner C | Per diem | 21 | 227 | 4767 | 0 | 21 | 227 | 4767 | 0 | 0%
#VALUE!
1.3.2 | Local (staff assigned to the Action) |  |  |  |  | #VALUE!
1.3.2.1 | Local perdiem - Partner B | Per diem | 528 | 35 | 18480 | 0 | 528 | 35 | 18480 | 0 | 0%
1.3.2.2 | Local perdiem - Partner A | Per diem | 528 | 35 | 18480 | 1520 | 500 | 40 | 20000 | 1520 | 8.225% | The upward variation in the budget line '1.3.2.2 Local per diem - Partner A' is primarily due to the considerable rise in the local rate of inflation. The annual inflation rate in Nigeria accelerated for the fifth month to 22.22% in April 2023, reaching a nearly 18-year high and following 22.04% in the prior month. Meanwhile, food inflation, which accounts for the bulk of Nigeria's inflation basket, climbed further to 24.61% in March from 24.45% in February, owing to increases in prices of oil and fat, bread and cereals, fish, potatoes, yam and other tubers, fruits, meat, vegetable, and spirits (source: https://tradingeconomics.com/nigeria/inflation-cpi). Therefore, a revision to reflect an increase from 35 to 40 per day is necessary to meet these new conditions and ensure smooth project execution.
#VALUE!
1.3.3 | Seminar/conference participants |  |  |  |  | #VALUE!
1.3.3.1 | Participant perdiem - Partner B | Per diem | 2460 | 20 | 49200 | -6000 | 2160 | 20 | 43200 | -6000 | -12.2%
1.3.3.2 | Participant perdiem - Partner A | Per diem | 2460 | 20 | 49200 | 0 | 2460 | 20 | 49200 | 0 | 0%
| Subtotal Human Resources |  |  |  | 342519 | 12542 |  |  | 355061 | 12542 | 3.662%
2 | Travel |  |  |  |  | #VALUE!
2.1 | International travel |  |  |  |  | #VALUE!
2.1.1 | International travel - Partner C | Per roundtrip | 3 | 1400 | 4200 | -1400 | 2 | 1400 | 2800 | -1400 | -33.33%
#VALUE!
2.2 | Local transportation |  |  |  |  | #VALUE!
2.2.1 | Local transportation - Partner B | Per month | 30 | 40 | 1200 | -1200 | 0 | 0 | 0 | -1200 | -100% | The total reduction in the budget line '2.2.1 Local transportation - Partner B' is a strategic budget reallocation designed to facilitate the acquisition of a dedicated project vehicle. In our ongoing effort to optimise our resources and improve operational efficiency, we have identified the need for a permanent mode of transportation, thereby eliminating the recurring local transportation costs / vehicle rent costs. This will also contribute to Partner B's organisational strengthening, since the project will leave a lasting contribution to its operational capacities. The acquisition of a project vehicle ensures reliable and timely transport, enhances our ability to plan and execute activities, and over the long term, presents a more cost-effective solution. Therefore, we are reallocating the entire budget previously set for local transportation (1,200 per month) towards this investment, resulting in a 100% decrease for this specific budget line.
2.2.2 | Local transportation - Partner A | Per month | 30 | 40 | 1200 | -400 | 20 | 40 | 800 | -400 | -33.33%
| Subtotal Travel |  |  |  | 6600 | -3000 |  |  | 3600 | -3000 | -45.45%
3 | Equipment and supplies |  |  |  |  | #VALUE!
3.1 | Purchase or rent of vehicles |  |  |  |  | 0
3.1.1 | Purchase of vehicles - Partner B | per vehicle | 1 | 0 | 0 | 23220 | 1 | 23220 | 23220 | 23220 | 100% | The budget line '3.1.1 Purchase of vehicles - Partner B' reflects a new allocation specifically earmarked for the acquisition of a project vehicle. As per our strategic decision to streamline operations and ensure mobility, we have deemed it necessary to invest in a dedicated vehicle for the project. The absence of this line in our original budget was a gap that required addressing. Therefore, we are introducing this new allocation amounting to 23,220 EUR, representing a 100% increase in this budget line. The availability of a project vehicle is expected to enhance operational efficiency, promote timely execution of project activities, and offer a long-term, cost-effective solution as opposed to recurring local transportation costs. This re-orientation in our budget allocation is a strategic investment aimed at strengthening our capacity to successfully implement the project as well as other future actions.
#VALUE!
3.1.2 | Rent of vehicles |  |  |  |  | #VALUE!
3.1.2.1 | Rent of vehicles - Partner B | Per month | 30 | 342 | 10260 | -10260 | 0 | 0 | 0 | -10260 | -100% | The budget line '3.1.2.1 Rent of vehicles - Partner B' shows a total reduction as a result of Partner B's strategic decision to procure a dedicated project vehicle, effectively making vehicle rentals redundant. This decision stems from analysis which showed that maintaining a rental agreement was not as cost-efficient nor as operationally advantageous in the long-term as compared to owning a project vehicle. Therefore, we have chosen to reallocate the entire budget initially set for vehicle rentals (10,260 per month) towards the purchase of a project vehicle, leading to a 100% decrease in this specific budget line. The project vehicle will enhance our operational efficiency, allow us to respond more effectively to project needs, and offer a more sustainable financial approach over the course of the project lifecycle. Thus, this budget revision is a calculated move towards better resource management and project execution.
3.1.2.2 | Rent of vehicles - Partner A | Per month | 30 | 342 | 10260 | 1710 | 35 | 342 | 11970 | 1710 | 16.67%
#VALUE!
3.2 | Furniture, computer equipment |  |  |  |  | #VALUE!
3.2.1 | Furniture, computer equipment - Partner B | Per office | 2 | 3087 | 6174 | -3087 | 1 | 3087 | 3087 | -3087 | -50%
3.2.2 | Furniture, computer equipment - Partner A | Per office | 2 | 3087 | 6174 | -3087 | 1 | 3087 | 3087 | -3087 | -50%
#VALUE!
3.3 | Machines, tools… |  |  |  |  | #VALUE!
#VALUE!
3.4 | Spare parts/equipment for machines, tools |  |  |  |  | #VALUE!
#VALUE!
3.5 | Other |  |  |  |  | #VALUE!
| Subtotal Equipment and supplies |  |  |  | 32868 | 8496 |  |  | 41364 | 8496 | 25.85%
4 | Local office |  |  |  |  | #VALUE!
4.1 | Vehicle costs |  |  |  |  | #VALUE!
4.1.1 | Vehicle costs - Partner B | Per month | 30 | 24 | 720 | -120 | 25 | 24 | 600 | -120 | -16.67%
4.1.2 | Vehicle costs - Partner A | Per month | 30 | 24 | 720 | 0 | 25 | 26 | 720 | 0 | 0%
#VALUE!
4.2 | Office rent |  |  |  |  | #VALUE!
4.2.1 | Office rent - Partner B | Per month | 30 | 142 | 4260 | -710 | 25 | 142 | 3550 | -710 | -16.67%
4.2.2 | Office rent - Partner A | Per month | 30 | 142 | 4260 | -710 | 25 | 142 | 3550 | -710 | -16.67%
#VALUE!
4.3 | Consumables - office supplies |  |  |  |  | #VALUE!
4.3.1 | Consumables - Partner B | Per month | 60 | 419 | 25140 | -12098 | 25 | 521.66 | 13042 | -12098 | -48.12% | We reduced the allocation to this budget line by 37.7% to free up funds for the purchase of a dedicated project vehicle, which we identified as a critical resource for our operation's efficiency and success. A revised analysis of our consumables usage over the previous projects indicated that we could achieve this reduction without adversely affecting our project's execution. By optimising the use of consumables, reducing waste, and improving procurement practices, we are confident we can maintain operations at a lower cost. Consequently, we have decreased the quantity from 60 to 30 months, which had been initially planned for office and activity use. This freed budget will be utilised towards the purchase of a project vehicle, enabling us to enhance our mobility and responsiveness to project needs.
4.3.2 | Consumables - Partner A | Per month | 60 | 419 | 25140 | -3000 | 60 | 369 | 22140 | -3000 | -11.93% | The revision for the '4.3.2 Consumables - Partner A' budget line represents a downward adjustment of 11.9%, which is primarily based on a strategic reassessment of our project priorities. After a careful analysis of our project's consumable usage, operational needs, and current priorities, we have determined that we can adjust the per-unit cost from 419 to 369 per month. This reduction aligns with our commitment to budget efficiency and optimising resource allocation, without compromising the project's outcomes. It also reflects our intention to invest funds strategically where they create the greatest impact. As a result, the budget allocation for this line item has been reduced by 3,000, freeing up these resources for reallocation to other priority areas of the project.
#VALUE!
4.4 | Other services (tel/fax, electricity/heating, maintenance) |  |  |  |  | #VALUE!
4.4.1 | Other services - Partner B | Per month | 30 | 300 | 9000 | -3300 | 25 | 228 | 5700 | -3300 | -36.67% | The budget line '4.4.1 Other services - Partner B' is subject to a downward revision of 24.0% as part of our broader strategy to redirect funds towards the purchase of a dedicated project vehicle. Following a comprehensive review of our expenses under this budget line, we identified potential savings through the reduction of some ancillary services that do not directly impact our project's core objectives. This budget optimisation process resulted in a reduction in the overall allocation from 9,000 to 6,840, releasing a total of 2,160. This saving is now allocated to finance the procurement of the project vehicle, which we anticipate will increase our operational efficiency and cost-effectiveness in the long run.
4.4.2 | Other services - Partner A | Per month | 30 | 300 | 9000 | -1500 | 25 | 300 | 7500 | -1500 | -16.67%
| Subtotal Local office |  |  |  | 78240 | -21438 |  |  | 56802 | -21438 | -27.4%
5 | Other costs, services |  |  |  |  | #VALUE!
5.1 | Publications |  |  |  |  | #VALUE!
5.1.1 | Publications - Partner B | Per unit | 500 | 5 | 2500 | -1900 | 200 | 3 | 600 | -1900 | -76%
5.1.2 | Publications - Partner A | Per unit | 500 | 5 | 2500 | -1900 | 200 | 3 | 600 | -1900 | -76%
#VALUE!
5.2 | Studies, research |  |  |  |  | #VALUE!
#VALUE!
5.3 | Expenditure verification/Audit |  |  |  |  | #VALUE!
5.3.1 | Expenditure verification - Partner C (overall project) | Per year | 3 | 8000 | 24000 | 0 | 2 | 12000 | 24000 | 0 | 0%
#VALUE!
5.4 | Evaluation costs |  |  |  |  | #VALUE!
5.4.1 | Baseline study - Partner C | Per unit | 1 | 10000 | 10000 | -3000 | 1 | 7000 | 7000 | -3000 | -30%
5.4.2 | Final evaluation - Partner C | Per unit | 1 | 15000 | 15000 | 3000 | 1 | 18000 | 18000 | 3000 | 20%
5.4.3 | Independent Monitoring, Evaluation, Accountability and Learning (MEAL) services including MEAL sytem as well as capacity development of staff and selected key stakeholders (e.g., local partners) - Partner C (overall project) | Per day | 47 | 677 | 31819 | -8124 | 35 | 677 | 23695 | -8124 | -25.53%
#VALUE!
5.5 | Translation, interpreters |  |  |  |  | #VALUE!
#VALUE!
5.6 | Financial services (bank guarantee costs etc.) |  |  |  |  | #VALUE!
5.6.1 | Financial services - Partner B | Per month | 30 | 40 | 1200 | -110 | 30 | 36.33 | 1090 | -110 | -9.167% | We reduced the allocation to this budget line by 9.2% to free up funds for the purchase of a dedicated project vehicle, which we identified as a critical resource for our operation's efficiency and success. A revised analysis of our bank guarantee cost over the previous projects indicated that we could achieve this reduction without adversely affecting our project's execution. Consequently, we have decreased the unit cost from 40EUR to 36.33EUR. This freed budget will be utilised towards the purchase of a project vehicle, enabling us to enhance our mobility and responsiveness to project needs.
5.6.2 | Financial services - Partner A | Per month | 30 | 40 | 1200 | 0 | 30 | 40 | 1200 | 0 | 0%
#VALUE!
5.7 | Costs of conferences/seminars |  |  |  |  | #VALUE!
5.7.1 | Accommodation services |  |  |  |  | #VALUE!
5.7.1.1 | Accommodation - Partner B | Per unit | 40 | 40 | 1600 | 200 | 45 | 40 | 1800 | 200 | 12.5%
5.7.1.2 | Accommodation - Partner A | Per unit | 40 | 40 | 1600 | 200 | 45 | 40 | 1800 | 200 | 12.5%
#VALUE!
5.7.2 | Catering services |  |  |  |  | #VALUE!
5.7.2.1 | Catering - Partner B | Per person/day | 3915 | 6 | 23490 | -11400 | 2015 | 6 | 12090 | -11400 | -48.53%
5.7.2.2 | Catering - Partner C | Per person/day | 200 | 8 | 1600 | 0 | 200 | 8 | 1600 | 0 | 0%
5.7.2.3 | Catering - Partner A | Per person/day | 3915 | 6 | 23490 | -4440 | 3175 | 6 | 19050 | -4440 | -18.9% | A modest increase of 1.5% has been made in the '5.7.2.3 Catering - Partner A' budget line to accommodate additional refreshment requirements for participants in certain activities that were not previously accounted for. Upon further evaluation of our programming, we recognised that some activities would benefit from the provision of refreshments to enhance participant engagement and satisfaction. Consequently, we have adjusted the per person/day allocation from 3,915 to 3,975, resulting in an overall increase of 360. This adjustment is intended to ensure that all participants are adequately catered for during the identified activities, thereby supporting a more conducive environment for learning and interaction.
#VALUE!
5.7.3 | Other event costs (e.g. facilitation, rental of venue and equipment) |  |  |  |  | #VALUE!
5.7.3.1 | Facilitation costs - Partner B | Per event | 131 | 100 | 13100 | 0 | 131 | 100 | 13100 | 0 | 0%
5.7.3.2 | Rental of Venue and Equipment - Partner B | Per event | 162 | 100 | 16200 | 2000 | 182 | 100 | 18200 | 2000 | 12.35%
5.7.3.3 | Facilitation costs for kick-off meeting - Partner C | Per event | 1 | 9800 | 9800 | 0 | 1 | 9800 | 9800 | 0 | 0%
5.7.3.4 | Facilitation costs of 3 annual review meetings - Partner C | Per event | 3 | 4600 | 13800 | 0 | 3 | 4600 | 13800 | 0 | 0%
5.7.3.5 | Facilitation costs - Partner A | Per event | 131 | 100 | 13100 | -3100 | 100 | 100 | 10000 | -3100 | -23.66%
5.7.3.6 | Rental of Venue - Partner A | Per event | 162 | 100 | 16200 | 0 | 162 | 100 | 16200 | 0 | 0%
#VALUE!
5.8 | Visibility actions |  |  |  |  | #VALUE!
5.8.1 | Visibility actions - Partner B | Per month | 30 | 240 | 7200 | -2400 | 20 | 240 | 4800 | -2400 | -33.33%
5.8.2 | Visibility actions - Partner C | Per month | 30 | 100 | 3000 | 0 | 30 | 100 | 3000 | 0 | 0%
5.8.3 | Visibility actions - Partner A | Per month | 30 | 240 | 7200 | 0 | 30 | 240 | 7200 | 0 | 0%
| Subtotal Other costs, services |  |  |  | 239599 | -30974 |  |  | 208625 | -30974 | -12.93%
6 | Other |  |  |  |  | #VALUE!
6.1 | Other - Partner B (third-party funding) | Per call | 1 | 19000 | 19000 | 0 | 1 | 19000 | 19000 | 0 | 0%
6.2 | Other - Partner A (third-party funding) | Per call | 1 | 19000 | 19000 | 0 | 1 | 19000 | 19000 | 0 | 0%
#VALUE!
| Subtotal Other |  |  |  | 38000 | 0 |  |  | 38000 | 0 | 0%
7 | Subtotal direct eligible costs of the Action (1-6) |  |  |  | 737826 | -34374 |  |  | 703452 | -34374 | -4.659%
8 | Indirect costs (maximum 7% of 7, subtotal of direct eligible costs of the Action) |  |  |  | 51648 | -2406 |  |  | 49242 | -2406 | -4.658%
9 | Total eligible costs of the Action, excluding reserve and volunteers' work (7+ 8) |  |  |  | 789474 | -36780 |  |  | 752694 | -36780 | -4.659%
10.1 | Provision for contingency reserve (maximum 5% of 7, subtotal of direct eligible costs of the Action) |  |  |  | 0 | 0 |  |  | 0 | 0 | 0%
10.2 | Volunteers' work |  |  |  | 0 | 0 |  |  | 0 | 0 | 0%
11 | Total eligible costs (9+10) |  |  |  | 789474 | -36780 |  |  | 752694 | -36780 | -4.659%
12.1 | Taxes |  |  |  | 0 | 0 |  |  | 0 | 0 | 0%
12.2 | Contributions in kind |  |  |  | 0 | 0 |  |  | 0 | 0 | 0%
13 | Total accepted costs of the Action (11+12) |  |  |  | 789474 | -36780 |  |  | 752694 | -36780 | -4.659%